## DETAILED
PROJECT: PROPOSED 3 DOORS FAMILY RESIDENTIAL HOUSE
LOCATION: 199 SITIO LAWLAWAN MASAGANA HOMES STA. RITA, GUIGUINTO, BULACAN
OWNER: MR. DAVID KENNETH JIMENEZ BOARAGAY
SUBJECT: BILL OF MATERIALS AND COST ESTIMATES
ITEM NO. | DESCRIPTION | QUANTITY |  | MATERIAL |  | LABOR & EQUIP. |  | TOTAL COST
|  | NO. UNITS | UNIT MEAS. | UNIT PRICE | TOTAL | UNIT PRICE | TOTAL
1 | DIVISION 1 - GENERAL REQUIREMENTS
| Mobilization | 1 | lot |  |  | 5000 | 5000 | 5000
| SUBTOTAL | [5 empty] | 5000 | 5000
2 | DIVISION 2 - SITE WORKS
a. | Site Clearing and Grubbing | 1 | lot |  |  | 2000 | 2000 | 2000
b. | Building Layout and Staking Out | 1 | lot |  |  | 2000 | 2000 | 2000
c. | Excavation
| Column Footing | 43.2 | cu.m
| Footing Tie Beam | 21.89 | cu.m
| Wall Footing | 23.52 | cu.m
| Septic Tank | 16.36 | cu.m
| Catch Basin | 2.05 | cu.m
|  | 107.02 | cu.m |  |  | 75 | 8026.5 | 8026.5
d. | Backfill and Compaction
| Column Footing | 39.6 | cu.m
| Footing Tie Beam | 16.39 | cu.m
| Wall Footing | 19.32 | cu.m
| Site Filling (for SOG) | 10.06 | cu.m
|  | 85.37 | cu.m |  |  | 100 | 8537 | 8537
e. | Earthfilling Materials |  | cu.m.
e. | Disposal and Hauling | 1 | lot |  |  | 2000 | 2000 | 2000
f. | Bedding and Soil Poisoning
| Column Footing | 3.51 | cu.m. | 730 | 2562.3
| Wall Footing | 5.7174 | cu.m. | 730 | 4173.702
| Footing Tie Beam | 4.368 | cu.m. | 730 | 3188.64
| Septic Tank | 1.193 | cu.m. | 730 | 870.89
| Catch Basin | 0.3328 | cu.m. | 730 | 242.944
| Slab on Grade | 13.078 | cu.m. | 730 | 9546.94
| Parking Area | 9.27 | cu.m. | 730 | 6767.1
| Soil Poisoning | 200 | sq.m. | 75 | 15000
| Labor Cost | 1 | lot |  |  | 2000 | 2000
[5 empty] | 42352.516 |  | 2000 | 44352.516
| SUBTOTAL |  |  |  | 42352.516 |  | 24563.5 | 66916.016
3 | DIVISION 3 - CONCRETE
a | Job-mixed, 3500 psi
| Column Footing | 3.6 | cu.m
| Wall Footing | 4.2 | cu.m
| Slab on Grade (Parking Area) | 7.8 | cu.m
| Column (Foundation to Roof Parapet) | 2.48 | cu.m
| Tie Beam | 3.22 | cu.m
| Roof Beam | 4.18 | cu.m
| Ground Floor Slab | 11.3 | cu.m
| Labor Cost | 36.78 | cu.m |  |  | 1200 | 44136
| Portland Cement | 226 | bags | 225 | 50850
| Crashed Gravel | 13.46 | cu.m. | 942 | 12679.32
| Washed Sand | 12.55 | cu.m. | 730 | 9161.5
[5 empty] | 72690.82 |  | 44136 | 116826.82
| SUBTOTAL |  |  |  | 72690.82 |  | 44136 | 116826.82
4 | DIVISION 4 - MASONRY
a | Masonry Unit
| 5" CHB | 3306 | pcs | 16 | 52896
b | Mortar Cell and Laying
| Portland Cement | 221 | bags | 225 | 49725
| Washed Sand | 25 | cu.m | 730 | 18250
c | Masonry Unit
| 4" CHB | 599 | pcs | 12 | 7188
d | Mortar Cell and Laying
| Portland Cement | 24 | bags | 225 | 5400
| Washed Sand | 3 | cu.m | 730 | 2190
| Labor Cost | 446 | sq.m |  |  | 120 | 53520
[5 empty] | 135649 |  | 53520 | 189169
| SUBTOTAL |  |  |  | 135649 |  | 53520 | 189169
5 | DIVISION 5 - METALS
5.1 | REINFORCING BARS
a. | Column Footing
| 12mm dia. X 6m Deformed Bars - grade 40 | 16 | pcs. | 220 | 3520
b. | Wall Footing (Inc. Boundary Fence)
| 10mm dia. X 6m Deformed Bars - grade 40 | 24 | pcs. | 175 | 4200
c. | Footing Tie Beam
| 12mm dia. X 6m Deformed Bars - grade 40 | 48 | pcs. | 220 | 10560
| 10mm dia. X 6m Deformed Bars - grade 40 | 52 | pcs. | 175 | 9100
d. | Column
| 12mm dia. X 6m Deformed Bars - grade 40 | 72 | pcs. | 220 | 15840
| 10mm dia. X 6m Deformed Bars - grade 40 | 48 | pcs. | 175 | 8400
e. | Masonry
| 10mm dia. X 6m Deformed Bars - grade 40 | 125 | pcs. | 175 | 21875
f. | Ground Floor Slab
| 10mm dia. X 6m Deformed Bars - grade 40 | 170 | pcs. | 175 | 29750
c. | Roof Beam
| 12mm dia. X 6m Deformed Bars - grade 40 | 43 | pcs. | 220 | 9460
| 10mm dia. X 6m Deformed Bars - grade 40 | 47 | pcs. | 175 | 8225
g. | Tie Wire
| #16 G.I. Wire 45kls/ rolls | 5 | rolls | 1800 | 9000
| Labor Cost | 1 | lot |  |  | 35000 | 35000
[5 empty] | 129930 |  | 35000 | 164930
5.2 | ROUGH HARDWARE
| Assorted CW Nails 4" | 1 | kegs | 1100 | 1100
| Finishing Nails 1" | 10 | kls. | 68 | 680
| Finishing Nails 1-1/2" | 10 | kls. | 66 | 660
| Hack Saw Blade | 10 | pcs. | 45 | 450
| Cement Pail | 5 | pcs. | 50 | 250
| 3" Concrete Nails | 5 | kls. | 90 | 450
[5 empty] | 3590 |  |  | 3590
5.3 | STEEL ROOF FRAMING
| Lump Sum | 1 | lot |  | 35000 |  |  | 35000
| SUBTOTAL |  |  |  | 168520 |  | 35000 | 203520
6 | DIVISION 6 - WOOD AND PLASTIC
6.1 | KITCHEN CABINET AND CLOSET
| Counter with Tiles, Base Cabinet | 3 | sets | 5000 | 15000 | 5000 | 15000
[5 empty] | 15000 |  | 15000 | 30000
6.2 | FORMWORKS AND SCAFFOLDINGS
| 400 - 2"x2"x12' Coco Lumber | 500 | bd.ft. | 45 | 22500
| 400- 2"x3"x12' Coco Lumber | 500 | bd.ft. | 45 | 22500
| 1/2" thk x 4'x8' Plywood | 58 | pcs. | 700 | 40600
[5 empty] | 85600 |  |  | 85600
| SUBTOTAL |  |  |  | 100600 |  | 15000 | 115600
7 | DIVISION 7 - THERMAL AND MOISTURE PROTECTION
7.1 | WATERPROOFING | [7 empty] | cr | 18sqm
| Cementitious Waterproofing | 18.15 | sqm | 500 | 9075 |  |  |  | 335
| Plexibond Waterproofing for firewall | 17 | gal | 860 | 14620 |  |  |  | firewall | 93 | sqm
| Cement | 10 | bags | 225 | 2250 |  |  |  | plexibond | 18.6 | gal | 74.4 | liters
| Labor Cost | 1 | lot |  |  | 5000 | 5000
[5 empty] | 25945 |  | 5000 | 30945 | cement | 9.672 | bags | 483.6 | kg
7.2 | ROOFING
a. | Panels and Bended Accessories
| Ga. 26, 0.4 Corrugated-type | 136.5 | sqm | 550 | 75075
| Metal Side Flashing, 0.40mm x 610mm L.S. | 82.5 | lm | 200 | 16500
| Metal Gutter, 0.4mm x 915mm L.S. | 13.2 | lm | 200 | 2640
| Installation of Roofing | 1 | lot |  |  | 20000 | 20000
[5 empty] | 94215 |  | 20000 | 114215
b. | Hardware Accessories
| Nail, Concrete 1-1/2" | 300 | pcs | 0.6 | 180
| Rivets, Blind 5/32" x 3/8" | 1900 | pcs | 0.5 | 950 |  |  |  | 1865.82
| Teckscrew Type "s", 12-24 x 25mm | 1500 | pcs | 1.1 | 1650
[5 empty] | 2780 |  |  | 2780
| SUBTOTAL |  |  |  | 122940 |  | 25000 | 147940
8 | DIVISION 8 - DOORS, WINDOWS AND GLASS
8.1 | Wood Doors (inc. jamb)
D1 | Tanguile Wooden Solid Panel Swing Door
| (1.0mW x 2.2mH) | 3 | sets | 8000 | 24000
D2 | Hollow Core Panel Door (0.9mW x 2.2mH) | 3 | sets | 7000 | 21000
D3 | Hollow Core Panel Door (0.9mW x 2.2mH) | 3 | sets | 7000 | 21000
D4 | PVC Door (0.7mW x 2.2mH) | 3 | sets | 2500 | 7500
| Installation Cost | 12 | sets |  |  | 600 | 7200
[5 empty] | 73500 |  | 7200 | 80700
8.2 | Windows
W1 | Swing Type Steel Casement Window
| 6mm Smoked Glass Window (1.5mW x 1.4mH) | 2 | sets | 5500 | 11000
W2 | Swing Type Steel Casement Window
| 6mm Smoked Glass Window (1.2mW x 1.4mH) | 2 | sets | 4500 | 9000
W3 | Swing Type Steel Casement Window
| 6mm Smoked Glass Window (0.9mW x 1.4mH) | 2 | sets | 4000 | 8000
W4 | Awning Type Steel Casement Window
| 6mm Smoked Glass Window (0.6mW x 0.6mH) | 3 | sets | 2000 | 6000
| Installation Cost | 9 | sets |  |  | 250 | 2250
[5 empty] | 34000 |  | 2250 | 36250
| SUBTOTAL |  |  |  | 107500 |  | 9450 | 116950
9 | DIVISION 9 - FINISHES | [10 empty] | 302 | 0.36 | 108.72 | cement | 144.87
9.2 | PLASTERING | [9 empty] | exterior | 302 | 0.02 | 6.04 | sand | 10.86
| Portland Cement | 113 | bags | 225 | 25425 |  |  |  | 543 | 13.575 | interior | 241 | 0.15 | 36.15
| Washed Sand | 13 | cu.m | 730 | 9490 | [6 empty] | 241 | 0.02 | 4.82
| Labor Cost | 543 | sq.m |  |  | 200 | 108600
[5 empty] | 34915 |  | 108600 | 143515
9.3 | FLOOR FINISHING
FF-1 | 600mm x 600mm Ceramic Tiles | 80 | sq.m. | 750 | 60000
FF-2 | 600mm x 600mm Non Skid Ceramic Tiles | 15 | sq.m. | 750 | 11250
FF-3 | 300mm x 600mm Matte Finish Ceramic Tiles | 9.6 | sq.m. | 850 | 8160
FF-4 | Rough Concrete Finish with 6mm groove | 71 | sq.m. | 400 | 28400
| Labor Cost | 175.6 | sq.m. |  |  | 200 | 35120
| Cement Tile Adhesive (Ordinary) | 35 | bags | 285 | 9975
| Tile Grout | 27 | bags | 150 | 4050
[5 empty] | 121835 |  | 35120 | 156955 |  | 893.8212
9.4 | WALL FINISHING
WF-1 | Semi-gloss Acrytex Paint - code for final approval | 3 | gal | 1050 | 3150
WF-2 | Semi-gloss Acrytex Paint - code for final approval | 36 | gal | 1050 | 37800
WF-3 | Semi Gloss Latex Paint - code for final approval | 37 | gal | 1000 | 37000
WF-4 | 300mm x 600mm Ceramic Tiles | 43.8 | sqm | 850 | 37230
WF-5 | 2" x 4" (6M) Tubular slats in Lacquer Paint Finish | 6 | pcs | 1200 | 7200
| Labor Cost | 482 | sqm |  |  | 200 | 96400
| Heavy Duty Tile Adhesive (25kg) | 15 | bags | 485 | 7275
| Tile Grout (2kg) | 9 | bags | 150 | 1350
[5 empty] | 131005 |  | 96400 | 227405
Miscellaneous
| Primer - Permacoat Flat Latex | 29 | gal | 550 | 15950
| Plasulux Glazing Putty | 5 | gal | 620 | 3100
| Concrete Neutralizer | 6 | gal | 450 | 2700
| Paint Thinner | 2 | gal | 470 | 940
| Sanding Sealer |  |  |  | 0
| Acry Color |  |  |  | 0
| Calsomine |  |  |  | 0
| Sandpaper #100 | 5 | mtr | 200 | 1000
| Sandpaper #180 | 5 | mtr | 200 | 1000
| Brushes | 1 | lot | 2000 | 2000
[5 empty] | 26690 |  |  | 26690
CEILING FINISHING
CF-1 | Hardie Flex 3/16" | 31 | pcs | 350 | 10850
CF-2 | Hardie Flex 3/16" | 4 | pcs | 350 | 1400
CF-3 | Metal Spandrel | 20 | sq.m | 1000 | 20000
| Metal Furring Ceiling Joist (19mm x 50mm x 5m) | 60 | pcs | 130 | 7800
| Carrying Channel (12mm x 38mm x 5m) | 30 | pcs | 120 | 3600
| Wall Angle (25mm x 25mm x 3m) | 46.2 | pcs | 35 | 1617
| Fasteners, screw, metal clip, hangers | 1 | lot | 7500 | 7500
| Labor Cost | 90 | sq.m |  |  | 300 | 27000
[5 empty] | 52767 |  | 27000 | 79767
FINISHING HARDWARE
| Yale Lockset | 12 | sets | 400 | 4800
| Dead Bolt | 3 | sets | 600 | 1800
| Door Stopper and Closer | 6 | sets | 950 | 5700
| 3-1/2" X 3-1/2" Loose Pin Hinges | 36 | sets | 70 | 2520
| Miscellaneous | 1 | lot | 1000 | 1000
[5 empty] | 15820 |  |  | 15820
| SUBTOTAL |  |  |  | 383032 |  | 267120 | 650152
10 | DIVISION 15 - PLUMBING
10.1 | FIXTURES
| Water Closet w/ fittings - One piece | 3 | sets | 7000 | 21000
| Wall hung Lavatory | 3 | sets | 4500 | 13500
| Handheld Bidet - Chrome finish | 3 | sets | 1500 | 4500
| Kitchen Stainless Sink | 3 | sets | 3500 | 10500
| Kitchen Faucet | 3 | sets | 800 | 2400
| Floor Drain Strainer | 12 | sets | 200 | 2400
| Shower Set | 3 | sets | 1500 | 4500
| Installation Cost | 30 | sets |  | 0 | 300 | 9000
[5 empty] | 58800 |  | 9000 | 67800
10.1 | WATER LINE
| BELDEN PPR Pipe PN20 020mm x 4m | 30 | pcs | 350 | 10500
BELDEN PPR Pipe PN20 025mm x 4m
BELDEN PPR Pipe PN20 032mm x 4m
| BELDEN GV 020 Gate Valve | 6 | pcs | 400 | 2400
| BELDEN GV 020 Check Valve | 3 | pcs | 400 | 1200
| BELDEN LF 020 1/2" Elbow Fem Adapter |  |  |  | 0
| BELDEN LL 020 Elbow 90° | 30 | pcs | 30 | 900
| BELDEN LL 025 Elbow 90° |  |  |  | 0
| BELDEN LL 032 Elbow 90 |  |  |  | 0
| BELDEN LR 025 x 020 Elbow Reducer |  |  |  | 0
| BELDEN SR 032 x 025 Straight Reducer |  |  |  | 0
| BELDEN TR 032 x 025 TEE Reducer |  |  |  | 0
| BELDEN TR 025 x 020 TEE Reducer |  |  |  | 0
| BELDEN PPR Coupling | 15 | pcs | 30 | 450
| BELDEN PPR Cap | 15 | pcs | 30 | 450
| BELDEN TT 020 TEE Equal | 33 | pcs | 30 | 990
| BELDEN TT 025 TEE Equal |  |  |  | 0
| BELDEN UP 032 UNION PATENTE Metal Joint |  |  |  | 0
| PPR Tools Set, Pipe Cutter and Circular | 1 | lot | 2000 | 2000
| Miscellaneous | 1 | lot | 2000 | 2000 | 5000 | 5000
[5 empty] | 20890 |  | 5000 | 25890
SEWER LINE - ULTIMA SANITARY PIPES
| SERIES 1000 110mm (4") X 3M | 18 | pcs | 540 | 9720
| SERIES 1000 63mm (2") X 3M | 12 | pcs | 190 | 2280
| SAN WYE 4" x 4" | 6 | pcs | 105 | 630
| SAN WYE REDUCER 4" x 2" | 24 | pcs | 90 | 2160
| SAN TEE 4" x 4" | 4 | pcs | 115 | 460
| SAN TEE 2" x 2" | 3 | pcs | 30 | 90
| COUPLING 110mm (4") | 6 | pcs | 45 | 270
| COUPLING 63mm (2") | 6 | pcs | 15 | 90
| CO ADAPTER W/ PLUG 110mm (4") | 12 | pcs | 45 | 540
| BEND 1/4 (90) DH (4") | 9 | pcs | 65 | 585
| BEND 1/8 (45) (4") | 6 | pcs | 65 | 390
| BEND 1/4 (90) DH (2") | 36 | pcs | 25 | 900
| BEND 1/8 (45) (2") | 12 | pcs | 20 | 240
| P-TRAP 63mm (2") | 18 | pcs | 70 | 1260
| P-TRAP WITH CLEANOUT 63mm (2") | 3 | pcs | 70 | 210
| SOLVENT 400 CC | 3 | qrts | 150 | 450
| MISCELLANEOUS | 1 | lot | 2000 | 2000 | 5000 | 5000
[5 empty] | 22275 |  | 5000 | 27275
DRAINAGE LINE ULTIMA SANITARY PIPES
| SERIES 1000, 150mm (6") x 3m |  | pcs
| SERIES 1000, 110mm (6") x 3m |  | pcs
| SERIES 1000, 90mm (3") x 3m |  | pcs
DRAINAGE LINE ULTIMA SANITARY PIPES
| SERIES 1000 110mm (4") X 3M | 5 | pcs | 540 | 2700
| COUPLING 110mm (4") dia. | 4 | pcs | 45 | 180
| SOLVENT 400CC | 2 | pcs | 150 | 300
| MISCELLANEOUS | 1 | lot | 2000 | 2000 | 2500 | 2500
[5 empty] | 5180 |  | 2500 | 7680
CATCH BASIN
| 4" thk CHB (4 sets 600mm x 60mm x 600mm) | 155 | pcs | 12 | 1860
| 6mx10mmØ RSB | 11 | pcs | 175 | 1925
| Cement | 8 | bags | 225 | 1800
| Sand | 1 | cu.m. | 730 | 730
| Gravel | 1 | cu.m. | 950 | 950
| Labor Cost | 4 | sets |  |  | 1500 | 6000
[5 empty] | 7265 |  | 6000 | 13265
SEPTIC TANK
| 4" thk CHB | 258 | pcs | 12 | 3096
| 6mx10mmØ RSB | 29 | pcs | 175 | 5075
| Cement | 25 | bags | 225 | 5625
| Sand | 3 | cu.m. | 730 | 2190
| Gravel | 2 | cu.m. | 950 | 1900
| Labor Cost | 1 | lot |  |  | 5000 | 5000
[5 empty] | 17886 |  | 5000 | 22886
| SUBTOTAL |  |  |  | 132296 |  | 32500 | 164796
10 | DIVISION 16 - ELECTRICAL
10.1 | WIRING DEVICES
| 1-Gang Switch | 3 | pcs | 220 | 660
| 2-Gang Switch | 6 | pcs | 220 | 1320
| 3-Gang Switch | 6 | pcs | 220 | 1320
| Duplex Convenience Outlet | 30 | pcs | 220 | 6600
| Aircon Outlet w/ grounding type | 3 | pcs | 220 | 660
| Refrigerator Outlet | 3 | pcs | 220 | 660
| Range Outlet | 3 | pcs | 220 | 660
| Washing Machine Outlet | 3 | pcs | 220 | 660
| GFCI Outlet | 6 | pcs | 1000 | 6000
| Installation Cost | 63 | pcs |  |  | 250 | 15750
[5 empty] | 18540 |  | 15750 | 34290
10.2 | LIGHTING FIXTURES
| 100mm dia. Surface mounted downlight - cool white | 9 | pcs | 250 | 2250
| 150mm dia. LED downlight - daylight | 15 | pcs | 250 | 3750
| 300mm dia. LED Ceiling mounted light - daylight | 3 | pcs | 750 | 2250
| Installation Cost | 27 | pcs |  |  | 250 | 6750
[5 empty] | 8250 |  | 6750 | 15000
10.3 | POWER SYSTEM
a. | Wires and Cables
| 5.5mm2 THHN Wire | 1 | roll | 4500 | 4500
| 3.5mm2 THHN Wire | 1 | roll | 3500 | 3500
| 2.0mm2 TW Wire | 1 | roll | 2500 | 2500
| Wiring Accessories | 1 | lot | 3000 | 3000
b. | Pipes and Boxes
| 20mm dia. PVC Pipe x 3m | 85 | pcs | 80 | 6800
| Junction Box 4"x4" | 35 | pcs | 50 | 1750
| Utility Box 2"x4" | 70 | pcs | 30 | 2100
| Labor Cost | 190 | pcs |  |  | 250 | 47500
| Conduit Fittings | 1 | lot | 3000 | 3000
| Consumable Materials | 1 | lot | 3000 | 3000
| Supports | 1 | lot | 3000 | 3000
[5 empty] | 33150 |  | 47500 | 80650
10.4 | MAIN FEEDER LINE
| 8mm2 THHN Wire | 1 | roll | 6000 | 6000
| 3.5mm2 TW Wire | 1 | roll | 2500 | 2500
| 20mm dia. RSC Pipe x 3m | 25 | pcs | 900 | 22500
[5 empty] | 31000 |  |  | 31000
10.5 | PANELBOARD
MAIN: 60/30/30AT, 225 AF, 1P, 230V
BRANCH 7-15 AT, 12-20AT
| NEMA 3R Enclosure MCB | 3 | sets | 2500 | 7500
| Installation Cost | 3 |  |  |  | 5000 | 15000
[5 empty] | 7500 |  | 15000 | 22500
| SUBTOTAL |  |  |  | 98440 |  | 85000 | 183440
1960309.836
| PREPARED BY: |  |  | CONFORME:
| RHINA MARIE C. MONFORTE, UAP |  |  | DAVID KENNETH J. BORAGAY
| Architect |  |  |  | Owner
License No. 0044218
Validity: 09/21/2024
PTR No. 8229965
Date: 02/04/2022
Issued at: Pasig, City
TIN No. 332-073-444

## SUMMARY
PROJECT: PROPOSED 3 DOORS FAMILY RESIDENTIAL HOUSE
LOCATION: 199 SITIO LAWLAWAN MASAGANA HOMES STA. RITA, GUIGUINTO, BULACAN
OWNER: MR. DAVID KENNETH JIMENEZ BOARAGAY
SUBJECT: BILL OF MATERIALS AND COST ESTIMATES
ITEM NO. | DESCRIPTION | TOTAL MATERIAL COST | TOTAL LABOR COST | TOTAL AMOUNT
1 | DIVISION 1 - GENERAL REQUIREMENTS |  | 5000 | 5000
2 | DIVISION 2 - SITEWORKS | 42352.516 | 24563.5 | 66916.016
3 | DIVISION 3 - CONCRETE | 72690.82 | 44136 | 116826.82
4 | DIVISION 4 - MASONRY | 135649 | 53520 | 189169
5 | DIVISION 5 - METALS | 168520 | 35000 | 203520
6 | DIVISION 6 - WOOD AND PLASTIC | 100600 | 15000 | 115600
7 | DIVISION 7 - THERMAL AND MOISTURE PROTECTION | 122940 | 25000 | 147940
8 | DIVISION 8 - DOORS AND WINDOWS AND GLASS | 107500 | 9450 | 116950
9 | DIVISION 9 - FINISHES | 383032 | 267120 | 650152
10 | DIVISION 15 - PLUMBING | 132296 | 32500 | 164796
11 | DIVISION 16 - ELECTRICAL | 98440 | 85000 | 183440
|  | 1364020.336 | 596289.5 | 1960309.836
| TOTAL PROJECT COST |  |  | 1960309.836
| PREPARED BY: | CONFORME:
| RHINA MARIE C. MONFORTE, UAP | DAVID KENNETH J. BORAGAY
| Architect |  | Owner
License No. 0044218
Validity: 09/21/2024
PTR No. 8229965
Date: 02/04/2022
Issued at: Pasig, City
TIN No. 332-073-444

## Sheet3
33.2 |  |  |  | 14.4 |  |  |  | 9.4
9.6 |  |  |  | 13.5 |  |  |  | 9.15
9.6 |  |  |  | 12.5 |  |  |  | 10
2.35 |  |  |  | 7.2 |  |  |  | 10
3.1 |  |  |  | 7.9 |  |  |  | 14.4
3.1 |  |  |  | 8.6 |  |  |  | 3.5
2.35 |  |  |  | 9.2 |  |  |  | 4.15
2.43 | [7 empty] | 4.15
2.43 |  |  |  | 73.3 | 0.075 | 5.4975 | ftb | 4.15
2.48 | [7 empty] | 4.15
2.48 | [7 empty] | 4.75
2.48 | [7 empty] | 2.7
2.8 | [7 empty] | 1.75
2.43 | [7 empty] | 1.75
2.43 | [7 empty] | 33.4
2.4 | [7 empty] | 4.1
2.4 | [7 empty] | 4.8
2.4 | [7 empty] | 126.3 | 0.045 | 5.6835 | roof beam
1.27
1.27
1.27
94.27 | 0.075 | 7.0703 | wall footing
3.95 |  |  |  | 3.51
2.95 |  |  |  | 5.7174
2.5 |  |  |  | 4.368
3.1 |  |  |  | 1.193
2.85 |  |  |  | 0.3328
2.45 |  |  |  | 13.078
2 |  |  |  | 28.1992 | gravel bedding
2.85
2.45
2.8
1.2
2.2
2.65
2.65
2.8
3.5
2.65
45.55 | 0.48 | 21.864 | footing tie beam excavation